## Project schedule initial
| Projet PFE |  |  |  |  | Project start: | [7 empty] | 2026-02-09 | [12 empty] | Project start: | [6 empty] | 2026-08-09
| PFE 2026 - AI-powered Chatbot for GitHub |  |  |  |  | Display week: | [7 empty] | 1
[6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01 | [6 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27 | [6 empty] | 2026-08-03 | [6 empty] | 2026-08-10
| TASK | PROGRESS | START | END | time axis 2026-02-09 to 2026-08-16
 | time axis 2026-02-09 to 2026-08-16
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cadrage et Architecture (Mois 1)
| Cadrage besoin ST + Choix Stack | 50% | 2026-02-09 | 2026-02-27 | 19
| Exploration Repo Github | 60% | 2026-02-10 | 2026-02-18 | 9
| Architecture RAG | 10% | 2026-02-18 | 2026-02-27 | 10 | [189 empty] | Le vecteur sert à chercher les chunks pertinents, le payload sert à filtrer et à construire la réponse en citant les bonnes sources
Collecte et prétraitement (Mois 2)
| Ingestion issues GitHub STM32Cube | 0% | 2026-03-02 | 2026-03-06 | 5
| Ingestion fichiers repos STM32Cube | 0% | 2026-03-07 | 2026-03-13 | 7
| Prétraitement (cleaning, chunking,métadonnées) | 0% | 2026-03-14 | 2026-03-31 | 18
Backend RAG (Mois 3)
| Vector DB + Indexation embeddings | 0% | 2026-04-01 | 2026-04-08 | 8
| Service de retrieval + API / Search | 0% | 2026-04-09 | 2026-04-22 | 14
| Affinage Scoring | 0% | 2026-04-23 | 2026-04-30 | 8
Intégration GenAI (Mois 4)
| Intégration LLM + service answer Question | 0% | 2026-05-01 | 2026-05-15 | 15
| Interface + Tests | 0% | 2026-05-15 | 2026-05-22 | 8
| Feedback + affinage prompt / filtres | 0% | 2026-05-23 | 2026-05-29 | 7
Amélioration , Evaluation (Mois 5)
| Evaluation (Jeu de tests) | 0% | 2026-06-01 | 2026-06-05 | 5
| Evaluation (mesures de qualité) | 0% | 2026-06-08 | 2026-06-12 | 5
| Filtres Avancés | 0% | 2026-06-15 | 2026-06-19 | 5
Finalisation, Documentation (Mois 6)
| Stablisation Technique | 0% | 2026-07-01 | 2026-07-10 | 10
| Rédaction rapport et documentation | 0% | 2026-07-13 | 2026-07-31 | 19
| Préparation démo et slides de soutenance | 0% | 2026-07-22 | 2026-08-09 | 19

## Project schedule dynamic
| Projet PFE |  |  |  |  | Project start: | [7 empty] | 2026-02-09 | [12 empty] | Project start: | [6 empty] | 2026-08-09
| PFE 2026 - AI-powered Chatbot for GitHub |  |  |  |  | Display week: | [7 empty] | 1
[6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01 | [6 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27 | [6 empty] | 2026-08-03 | [6 empty] | 2026-08-10
| TASK | PROGRESS | START | END | time axis 2026-02-09 to 2026-08-16
 | time axis 2026-02-09 to 2026-08-16
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cadrage et Architecture (Mois 1)
| Cadrage besoin ST + Choix Stack | 100% | 2026-02-09 | 2026-02-27 | 19
| Exploration Repo Github | 80% | 2026-02-10 | 2026-02-18 | 9
| Architecture RAG | 90% | 2026-02-18 | 2026-02-27 | 10 | [189 empty] | Le vecteur sert à chercher les chunks pertinents, le payload sert à filtrer et à construire la réponse en citant les bonnes sources
Collecte et prétraitement (Mois 2)
| Ingestion issues GitHub STM32Cube | 40% | 2026-03-02 | 2026-03-06 | 5
| Ingestion fichiers repos STM32Cube | 20% | 2026-03-07 | 2026-03-13 | 7
| Prétraitement (cleaning, chunking,métadonnées) | 30% | 2026-03-14 | 2026-03-31 | 18
Backend RAG (Mois 3)
| Vector DB + Indexation embeddings | 0% | 2026-04-01 | 2026-04-08 | 8
| Service de retrieval + API / Search | 0% | 2026-04-09 | 2026-04-22 | 14
| Affinage Scoring | 0% | 2026-04-23 | 2026-04-30 | 8
Intégration GenAI (Mois 4)
| Intégration LLM + service answer Question | 0% | 2026-05-01 | 2026-05-15 | 15
| Interface + Tests | 0% | 2026-05-15 | 2026-05-22 | 8
| Feedback + affinage prompt / filtres | 0% | 2026-05-23 | 2026-05-29 | 7
Amélioration , Evaluation (Mois 5)
| Evaluation (Jeu de tests) | 0% | 2026-06-01 | 2026-06-05 | 5
| Evaluation (mesures de qualité) | 0% | 2026-06-08 | 2026-06-12 | 5
| Filtres Avancés | 0% | 2026-06-15 | 2026-06-19 | 5
Finalisation, Documentation (Mois 6)
| Stablisation Technique | 0% | 2026-07-01 | 2026-07-10 | 10
| Rédaction rapport et documentation | 0% | 2026-07-13 | 2026-07-31 | 19
| Préparation démo et slides de soutenance | 0% | 2026-07-22 | 2026-08-09 | 19

## New GANTT
| Projet PFE |  |  |  |  | Project start: | [7 empty] | 2026-02-09 | [12 empty] | Project start: | [6 empty] | 2026-08-09
| PFE 2026 - AI-powered Chatbot for GitHub |  |  |  |  | Display week:
[6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01 | [6 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27 | [6 empty] | 2026-08-03
| TASK | DEPENDANCES | PROGRESS | START | END | time axis 2026-02-02 to 2026-08-09
 | time axis 2026-02-02 to 2026-08-09
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cadrage et Architecture (Mois 1)
| Analyse besoin ST + contraintes moteur RAG interne | aucune | 50%
| Exploration repos GitHub | aucune | 80%
| Architecture globale de la solution | aucune | %
Pipeline de données (Mois 2)
| Ingestion issues GitHub | aucune | 40%
| Ingestion fichiers de Repos | aucune | 20%
| Cleaning issues + test | aucune | %
| Cleaning docs + test | aucune | %
| Schéma commun + métadonnées STM32Cube | Cleaning issues, Cleaning docs | %
| Génération chunks V1 | Schéma commun + métadonnées | 10%
Custom RAG & Préparation ST RAG (Mois 3)
| Custom RAG - Conception règles de chunking V2 (tailles, paragraphes, etc.) | PC hors domaine ST | 0%
| Custom RAG - Génération chunks V2 (issues + docs) | PC hors domaine ST | 0%
| ST RAG - Préparation corpus STM32Cube pour ingestion ST | Accès outil ST | 0%
Intégration & Évaluation automatisée (Mois 4)
| ST RAG – Tests d’ingestion | Génération corpus ST | 0%
| Custom RAG – Embeddings + index vectoriel | PC dispo, chunks V2 | 0%
| Custom RAG – Pipeline question/réponse (retrieval + génération) | Embeddings + index | 0%
| Custom RAG – Interface de test | Pipeline Q/R | 0%
| ST RAG – API question/réponse (scripts de test) | Tests ingestion ST | 0%
| Éval – Définition jeu de questions STM32Cube (scénarios réalistes) | Besoin ST, pipeline OK | 0%
| Éval – Scripts d’évaluation auto (appel 2 systèmes + stockage réponses) | Custom RAG Q/R, API ST, jeu de questions | 0%
Évaluation & Comparaison (Mois 5)
0%
0%
0%
Finalisation, Documentation, Soutenance (Mois 6)
0%
0%
0%

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.